## Sheet1
Project Title: |  | Activity Plan | Date of Preparation of Activity Plan:
Fashion Star |  | Prepared
Sr. | Task | By: | Actual Start | Actual | Team Mate Names | Status
No. |  |  | Date | Days
1 | Introduce |  | 2024-04-02 | 1 | All members | Completed
2 | Problem Definition |  | 2024-04-02 | 1 | All members | Completed
3 | Requirement & Non-functional requirement |  | 2024-04-02 | 1 | All members | Completed
4 | Process Analyst & Task sheet review | All Members | 2024-04-02 | 1 | All members | Completed
5 | Entity Relationship Diagram |  | 2024-04-02 | 1 | All members | Completed
6 | Data Flow Diagram |  | 2024-04-02 | 1 | All members | Completed
7 | Use Case Diagram & Algorithms |  | 2024-04-02 | 1 | All members | Completed
8 | Authentication Page (Web +API + Mobile): Login, Register, | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In Process
Forgot Password
9 | Account Page (APP + API + Mobile): | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
Edit Information, Change
Password, Edit State
10 | Home Page (APP + API + mobile ): Display All information: About us, introduce, contact us | Trương Ngọc Minh Cát | 2024-04-02 | 3 |  | In process
11 | Product Page (Web + API + Mobile): Show all products | Trương Ngọc Minh Cát | 2024-04-02 | 3 |  | In process
12 | Product Detail Page(Web + API + Mobile ): Show details of specific product | Trương Ngọc Minh Cát | 2024-04-02 | 3 |  | In process
13 | Cart Page (Web + API + Mobile): show all added items in cart | Trương Ngọc Minh Cát | 2024-04-02 | 3 |  | In process
14 | Order Page (Web + API + Mobile ): show order page and check out | Trương Ngọc Minh Cát | 2024-04-02 | 3 |  | In process
15 | Payment: (Web + API + Mobile ): create the payment Paypal and VNPAY for orders | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
16 | Order History and Status Page: show all orders | Trương Ngọc Minh Cát | 2024-04-02 | 3 |  | In process
17 | Create Store: make the store seller | Nguyễn Phương Hoa | 2024-04-02 | 3 |  | In process
18 | Create Category : (Web + API ): make level of categories for products | Nguyễn Phương Hoa | 2024-04-02 | 3 |  | In process
19 | Create products: (Web + API ) : make products to post via platform for customers | Nguyễn Phương Hoa | 2024-04-02 | 3 |  | In process
20 | Image Page: (Web + API): create the images for products | Nguyễn Phương Hoa | 2024-04-02 | 3 |  | In process
21 | Order Manage Pages : (Web + API + Mobile ): manage all orders of customers of shop | Nguyễn Phương Hoa | 2024-04-02 | 3 |  | In process
22 | Option Manage Page : (Web + API): manage all options for products | Nguyễn Phương Hoa | 2024-04-02 | 3 |  | In process
23 | Account Manage page : (Web + API): admin will manage all accounts of sellers, customers and shippers | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
24 | Variant page (Web + API): admin will manage all variant of products, request seller to do properly with variant or banned those variants | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
25 | Product page (Web + API): admin will manage all product of products, request seller to do properly with variant or banned those products | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
26 | Store page (Web + API): admin will manage requests of registering store, request seller to do properly or not allow those informations | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
27 | Statistic page: making report of statistic orders in the period of the days. | Phạm Quốc Chiến | 2024-04-02 | 3 |  | In process
28 | Shipper app screen register :(Mobile + API) shipper will register with his account | Lương Hữu Nhân | 2024-04-02 | 3 |  | Not Available
29 | Shipper home screen (Mobile + API) : show all details of screens | Lương Hữu Nhân | 2024-04-02 | 3 |  | Not Available
30 | Order screen (Mobile + API): shipper will receive orders and entering the code of parcels to gain the order | Lương Hữu Nhân | 2024-04-02 | 3 |  | Not Available
31 | Confirm Screen (Mobile + API ): shipper will confirm orders when he/she finishes the shipping | Lương Hữu Nhân | 2024-04-02 | 3 |  | Not Available
32 | Chat room page Screen (WEB+ Mobile + API ): | Lương Hữu Nhân | 2024-04-02 | 3 |  | Not Available
* red: not attending